## Task Plan
ShopSphere ¦ Submission Task Plan
Project status reviewed 2026-10-09 ¦ Submission target: 2026-10-10 ¦ Current code and verification status.
Priority guide: P0 = core purchase/submission-critical; P1 = supporting or production-readiness. Completed dates use repository milestones; verification tasks are scheduled for Oct 9–10.
Done | 10 | Implemented | 4 | Verify | 2 | Total | 16
ID | Workstream | Priority | Description | Implementation status | Owner | Status | Start Date | End Date
D-01 | Completed | P0 | Product catalog and details | Product listing, categories, pricing and product-detail pages are implemented. | — | Done | 2026-10-07T00:00:00.000Z | 2026-10-07T00:00:00.000Z
D-02 | Completed | P0 | Stock-aware catalog | Server-side search, category, sort, pagination and current-stock availability are implemented. | — | Done | 2026-10-08T00:00:00.000Z | 2026-10-08T00:00:00.000Z
D-03 | Completed | P0 | Shopping bag | Redis-backed basket supports quantity changes and available-stock limits. | — | Done | 2026-10-07T00:00:00.000Z | 2026-10-07T00:00:00.000Z
D-04 | Completed | P0 | Checkout and order creation | Backend validates orders, calculates Catalog prices and safely handles checkout retries. | — | Done | 2026-10-07T00:00:00.000Z | 2026-10-07T00:00:00.000Z
D-05 | Completed | P0 | Inventory lifecycle | Inventory reserves stock atomically, commits on payment and releases on failure or expiry. | — | Done | 2026-10-07T00:00:00.000Z | 2026-10-07T00:00:00.000Z
D-06 | Completed | P0 | Asynchronous order messaging | Transactional outbox/inbox, retries and duplicate handling are implemented; broker outage recovery still needs rehearsal. | — | Done | 2026-10-07T00:00:00.000Z | 2026-10-07T00:00:00.000Z
D-07 | Completed | P0 | Demo and Stripe Test Mode payments | Hosted Stripe Checkout and signed completion/expiry webhooks passed local Test Mode verification. | — | Done | 2026-10-08T00:00:00.000Z | 2026-10-08T00:00:00.000Z
D-08 | Completed | P0 | Registration, login, and seeded admin | Email/password registration, login, seeded administrator and Gateway ownership checks are implemented. | — | Done | 2026-10-08T00:00:00.000Z | 2026-10-08T00:00:00.000Z
D-09 | Completed | P1 | Admin store management | Admin can manage products, stock adjustments/history, orders and revenue. | — | Done | 2026-10-08T00:00:00.000Z | 2026-10-08T00:00:00.000Z
D-10 | Completed | P1 | MinIO product image storage | Product images upload to S3-compatible MinIO storage from the admin portal. | — | Done | 2026-10-08T00:00:00.000Z | 2026-10-08T00:00:00.000Z
T-08 | Submission check | P0 | RabbitMQ outage recovery | Outbox/inbox and retries are implemented; the RabbitMQ interruption/recovery scenario has not yet been verified. | HungNP52 | Needs verification | 2026-10-09T00:00:00.000Z | 2026-10-10T00:00:00.000Z
T-15 | Submission check | P0 | Clean-stack and checkout rehearsal | Recorded CI and Compose configuration/image checks passed; a fresh local stack rehearsal remains unverified because Docker was unavailable. | HungNP52 | Needs verification | 2026-10-09T00:00:00.000Z | 2026-10-10T00:00:00.000Z
T-01 | Completed | P1 | Google sign-in account persistence | Google OAuth persists verified accounts by a digest of Google's stable subject, refreshes profile/last-login fields, and includes an EF migration and model tests. | HungND141 | Implemented | 2026-10-09T00:00:00.000Z | 2026-10-09T00:00:00.000Z
T-05 | Completed | P1 | Customer email delivery | MailKit SMTP supports TLS, retries and a durable event-ID ledger; Console simulation remains the local default. | HungND141 | Implemented | 2026-10-09T00:00:00.000Z | 2026-10-09T00:00:00.000Z
T-06 | Completed | P1 | Deployment security hardening | Production startup guards validate HTTPS, service secrets/TLS, persistent Gateway key storage, S3 and live Stripe settings; no production deployment was exercised. | HungNP52 | Implemented | 2026-10-09T00:00:00.000Z | 2026-10-09T00:00:00.000Z
T-07 | Completed | P1 | Live payment operations | Stripe test/live matching and admin Checkout Session reconciliation are implemented; no live transaction was tested and reconciliation does not issue refunds. | HungND141 | Implemented | 2026-10-09T00:00:00.000Z | 2026-10-09T00:00:00.000Z